## WW
Project | Scope of Project | Objective | Target | Metrics | Action | Cost / Budget(Rs) | Desired Results | AWS Outcome | Responsible | Accountable | Start Date | End Date | Status | Risk Mitigation / Opportunity Creation | Completion Status
Saving water from safety drill conducted at the site | Internal | To save water by providing a storage tank to collect water used for safety drills. | Water saving of 200 m3/yr | Water savings data | Provide storage tank for water storage | 100K | Water saving of 200 m3/yr | Sustainable Water Balance, Good water governance | Zakir | Hammad | 2025-01-01 | 2025-12-31 | Completed | Physical | 100%
ETP Recovery in Cooling tower | Internal | To use water in cooling tower from ETP plant | Water saving of 750 m3/yr | Water savings data | Improve the performance of ETP. | 11 Million | Water saving of 750 m3/yr | Sustainable Water Balance, Good water governance | Zakir | Hammad | 2025-06-30 | 2026-03-31 | In progress | Physical | 40%
Replacement of Stream Traps on condensate line | Internal | To replace steam traps and maximize the condensate collection. | Water saving of 650 m3/yr | Water savings data | Replace steam traps and maximize the condensate collection. | 9 Million | Water saving of 650 m3/yr | Sustainable Water Balance, Good water governance | Tayyab | Hammad | 2025-06-30 | 2025-02-28 | Completed | Physical | 100%
Utilization of condensate water in Utilities plant | Internal | To enhance onsite condesate water collection capability | Water saving of 980 m3/yr | Water savings data | To install a tank of 500o gallon capacity along with all its ancilaries to ensure water supply in utility plant. | 8 Million | Water saving of 650 m3/yr | Sustainable Water Balance, Good water governance | Tayyab | Hammad | 2025-06-30 | 2025-02-28 | Completed | Physical | 100%
Centarlized monitoring of water flow meter | Internal | Centarlized monitoring of water flow meter | Water saving of 1500 m3/yr | Water savings data | Installation of of complete infrastructure (cables, router, servers etc) to fcailiitate the centralized water monitoring framework. | 15.6 Million | Water saving of 1500 m3/yr | Good water governance, Sustainable water balance | Zakir | Hammad | 2025-01-01 | 2025-05-01 | Completed | Physical | 100%
Recovery of UF reject water | Internal | Recovery of UF reject water | Water saving of 200 m3/yr | Water savings data | Installation of pipework and a centrifugal pump (2 hp) to facilitate the transfer of UF reject water in collection tank. | 0.5 million | Water saving of 200 m3/yr | Good water governance, Sustainable water balance | zakir | Hammad | 2025-12-01 | 2026-01-01 | Completed | Physical | 100%
Stakeholder Engagement and Involvement | External | To improve water balance through knowledge sharing on water saving | Identify shared water challenges from stakeholders | Photographic evidence | Interview stakeholders to share learning and identify shared water challenges | 0 | Improve water balance and work on shared water challenges | Good water governance, Sustainable water balance | Saad | Hammad | 2025-10-01 | 2025-11-30 | Completed | Physical / Reputational | 100%
Cleaning Drive at keenjhar lake | External | To preserve natural resources, safer environment, save marine animals | Clean the lake and outskirts | Photographic evidence | Conduct a lake cleaning activity in collaboration with local authorities | 0 | Preserve natural resources, safer environment, save marine animals | Safer Environment, Good water governance | Tayyab | Abdullah | 2025-10-01 | 2025-11-30 | Completed | Regulatory / Financial / Physical | 100%
Setting an effluent discharge target below the local regulatory limit. | Internal | Set an effluent discharge target that is 10% below the applicable local regulatory limit. | 10% reduction in all discharge water KPI | EHS audit slides | Perform a through claening of ETP's UF membrane and installtion of dosing system in ETP plant. | 0 | 10% reduction in all discharge water KPI | Good water quality status | Tayyab | Hammad | 2025-06-01 | 2025-11-30 | Completed | Regulatory / Financial / Physical | 100%
Identify key suppliers to engage with to understand overall water footprint and explore water consumption reduction options. Interact with vendors and seek information on their water usage and risks. | External | To reduce usage of indirect water (30,000 cubic meter) by sharing best practices with the site. | 200 cubic meter of water reduction | Email | Perform a session with key suppliers to engage with to understand overall water footprint and explore water consumption reduction options | 0 | 200 cubic meter reduction | Good water quality status | Indirect | Key supplier | 2025-06-01 | 2026-03-31 | In progress | Regulatory / Financial / Physical | 80%
Performance Against Target
|  | Total Actions | 10
|  | Completed Actions | 8
|  | In Progress | 2
|  | Percent Completion | 80%