## Sheet1 (hidden)
Water Availability
Water Quality
WASH
Water Balance and Water Costs
Extreme Weather and Incident Response
On-site Wastewater and Stormwater Discharge
Stakeholder Engagement
Legal Requirements & Water Governance
Indirect Water Use

## Revision
Revision No. | Update Date | Update Context
1 | 2025-04-01 | The First Version of the Water Stewardship Plan
2 | 2025-09-01 | For updating actions in Water Stewardship Plan

## Korangi
GSK Pakistan (Korangi) Water Stewardship Action Plan
| Issue/Opportunities (in no particular order of importance) | Type(s) of Issue/Opportunity (physical, reputational, regulatory) | Shared Challenge in the Catchment? (Yes/No) | Description of Potential Negative Impact(s) on Site / Catchment | Likelihood of Negative Impact Materializing (4-very likely, 3-likely, 2-unlikely, 1-very unlikely) | Potential Severity of Impact for Site (3-high/2-medium/1-low) | Overall Risk Rating (Amber: <=6, Red >6) | Site Action | AWS Outcome Alignment | Target completion date | Progress Check | Responsible Person | Accountable Person | Financial Budget Allocation | Business Impact if the Risk Materializes | Target | Value Creation | Shared Value Benefit | Performance Management
1 | Water Availability | Physical + Reputational + Regulatory | Yes | Continuous depletion in the groundwater level might result in Site not meeting its water requirements. This poses a threat to Site’s water availability which would impact operations resulting in loss of business. Irregularities in raw material supply by suppliers (facing water challenges) which are in the same catchment of Site. Lack of adequate water may also impact the Site biodiversity. Inadequate water supply may compromise access to WASH for employees and communities. | 4 | 3 | 12 | 1. Monitor water stress annually at the catchment level to take preparedness against anticipated risks (e.g., by engaging local authorities with access to such data). |  | 31st December 2025 | In Progress | Abdullah Sagheer (Water Project Manager) | Masood Khan (Site Director) | GSK has entered in a mutti-million dollar partnership with WWF where WWF will be conducting surveys on catchment level to get ground water level and quality data. | Possible Loss of Production with volume reduction incase site doesn’t plan accordingly for depleting water levels. | Get Catchment Level Data for Malir River Catchment | Will help GSK in analysizing water challenges and take proactive measures | This action provides Environmental, Ecological, Economic benefits as it helps in understanding water availability and planning conservation efforts. | In Progress, co-ordinate with WWF. Escalate to regional team if support needed.
[8 empty] | 2. Update the Site's Business Continuity Plan (BCP) to cover all potential water-related issues |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | In case the Risk of Water Shortage Materailizes, Site will not have a proper plan for dealing with the risk. | To ensure operational continuity incase of water unavailability | Will help GSK in being proactive in its approach to take actions against water related challenges. | This action provides Environmental, Economic, Ecological benefits as it reduces dependency on external water sources and saves costs. | Done
[8 empty] | 3.Check Feasability rainwater harvesting on-site to reuse harvested rainwater for productive use within the Site boundary and reduce the volume of freshwater sourced. 3.1 Identify authorized third-party private tanker suppliers and establish supply during drought situations. |  | 5th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 3.5 Million is allocated for pilot project of rain water harversting | Incase the ground wate level depletes, site will not be able to rely on tanker water as well for backup supply leading to production losses. | Rain Water Harvesting would help site achieve savings of 1000 m3 on annual basis | Will help in achieving water waterfall targets as part of sustainability initiative from GSK Regional Team | This action provides Economic, Environmental benefits because it promotes efficient water use and reduces operational costs. | Done
[8 empty] | 4. Continue to identify opportunities to reduce / conserve water (e.g. installation of recovery plant for RO reject water) |  | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Site has identified oppourtunities to reduce water consumption and has identified projects against it. Details are as mentioned with each project. | Increased Water Consumption with more reliance on water tankers leading to increased costs. | Idenitification of Water Saving Initiatives along with their cost benefits | Will help in achieving its global sustainability targets as part of its initiative to reduce its water consumption from 2020 baseline by 20% till 2030. | This action provides Economic, Environmental benefits because it promotes efficient water use and reduces operational costs. | Done
|  |  |  | Steadily declining ground water resources may encourage the regulators to implement stringent regulations/ limitations on industrial water use, which may impact Sites water supply and increase overall water costs. | 4 | 3 | 12 | 5. Conduct annual awareness training session on water stewardship and water conservation practices for all Site employees. |  | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Site employees will not be familiar with Water conservation practices leading to increased water consumption due to behavioral issues leading to increased water costs. | Ensure Awareness among site empolyees of the Water Conservation practices so that they can implement the same ensuring best practices are translated in Catchment. | Responsible Water Utilization & Awareness amongst the site employees. | This action provides Social, Environmental benefits because it helps educate employees to adopt sustainable water practices. | Done
[8 empty] | 6. Site to assess the Current Water Storage Capacity and check feasability for Water Storage Capacity Increase. |  | 1st July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 10 Milllion will be required incase Site requires to increase its water capacity. | In case of water unavailability and lack of storage, site not be able to cater for prodcution volume due to lack of capacity. | Site to assess current water storage facility and upgrade it if deemed inadequate | Helping GSK to tackle operations in case of water scarcity | This action provides Economic, Environmental benefits because it ensures adequate water storage to support operations. | Done
[8 empty] | 7. Site to engage with Stakeholders for sharing of information and best practices |  | 31st March 2026 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses. | Engage with stakeholders to collectively reduce water consumption on catchment level by sharing best practices. | Help interact with stakeholders and collectively work for ensuring sustainable water use in the catchment | This action provides Social, Environmental, Ecological benefits because it fosters collaboration for sustainable water use. | In progress, escalate to Site Leadership team for support if required.
[8 empty] | 8. Site to assess commercial feasability for installation of piezometers for monitoring ground water level 8 8.1 Site to assess feasability for installation of additional borewell. |  | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 3 Million is estimated for piezometer installation while budget of over 80 Million will be required for new borewell. | Possible Loss of Production with volume reduction incase site doesn’t plan accordingly for depleting water levels of the current bores. | To ensure site can adapt incase of depleting water levels of borewells | Helping GSK to tackle operations in case of water scarcity and help in better monitoring of data from borewells. | This action provides Environmental, Economic benefits because it prepares site for water scarcity scenarios. | Done
| Water Quality |  |  | Site might have to invest in better equipment, filters, and chemicals which might increase the cost to operate the water purification systems in the plant. Low water quality may trigger regulatory risks such as more stringent water regulations being imposed in the region. Also, health risks to the Plants' water and the nearby community (Site provides drinking water to the nearby community) cannot be ruled out Poor water quality may also result in an impact on the nearby communities as well as IWRA's and imply a potential reputational risk for the industries operating in the area as a possible association with poorly performing industrial users. Poor water quality may impact product quality and brand reputation | 4 | 3 | 12 | 1. Site to engage with stakeholders for share informmation, best practices and possible areas of collaboration. |  | 31st March 2026 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses. | Collectively strengthen water quality on catchment level by sharing best practices. | Help interact with stakeholders and collectively work for ensuring sustainable water use in the catchment | This action provides Environmental, Ecological, Social benefits because it helps improve water quality through shared knowledge. | In Progress.
|  |  |  | The Site is dependent on the groundwater for all of its operations. In case of any quality issue, the operations will be affected until alternative sources are found. Further, Site might also have to increase the frequency of monitoring water on-site for comprehensive suite of analytes. | 2 | 2 | 4 | 3. Site to include important parameters in contract for Tanker Water Provider and test for the same. 3.1 Site to treat water from tap (accessed by the community) for comprehensive suite of analytes as mentioned in the NSDWQ/SSDWQ 3.2. Site to treat water from discharge of effluent treatment plant for required parameters of SEQS. |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Risk of impact on product quality incase the tanker water is not as per requirement. Also incase the drinking water is not as per requirement of SSDWQ, employee health will be impacted leading to more on job sickness leaves impacting site operations . | Ensure Tanker Water pH is below 7.5. Ensure Drinking water TDS is below 350 mg/l | Ensure water quality is as per local regulatory requirement ensuring compliance to legal requirements and ensuring access to clean drinking water to site employees. | This action provides Environmental, Social benefits because it ensures safe drinking water for health. | Done
[8 empty] | 4.Adjust the testing frequency of borewell water (monthly or quarterly basis) for a comprehensive suite of analytes (SSDWQ), as deemed necessary, based on the observed trends in water quality. |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 500,000 needed for bore water testing. | In case the bore water quality depletes, site will have to find corrective solution to ensure that site Reverse Osmosis Plant is operational. In case the RO Plant shuts down, complete site operations will be hampered. | Ensure Bore Water is as per required quality requirement ensuring smooth running of utility operations. | Ensure water quality monitoring is done at the source of water ensuring smooth operations access to clean drinking water to site employees. | This action provides Environmental, Economic benefits because it maintains water quality for operational use. | Done
[8 empty] | 5. Regularly clean and inspect the water storage tanks on-site to prevent microbial growth and contamination. |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No financial budget needed. Site performs inhouse maintenance and inspection of water storage tanks. | Impact on Stored Water Quality incase of microbial growth in water storage tanks impacting site operations. | Ensure Water Storage tanks are maintained as per requirement | Ensure access to clean drinking water by regular cleaning if underground storage water tanks. | This action provides Environmental, Economic benefits because it prevents contamination and ensures water quality. | Done
3 | WASH | Physical + Reputational + Regulatory | Yes | Poor access to WASH amenities at the catchment might impact the health of the Site's employees, Contractual staff, and other stakeholders related to the Site. This can affect the productivity of the employees, make them vulnerable to diseases. Inadequate WASH conditions can deteriorate the quality of the surface water and impact the communities relying on that water source. | 3 | 2 | 6 | 1. Ensure proper access to WASH is provided at the Site. 1.1 Conduct awareness session for employees on WASH. |  | 10th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No financial budget needed. | Impact on WASH services at site impacting the hygiene facilities at site. | Ensure WASH Services are regularly maintained at site. | Improved employee health and well-being by reducing risks associated with poor hygiene and sanitation and demonstrate GSK’s commitment to sustainability and employee welfare, aligning with corporate responsibility goals. | This action provides Social, Environmental benefits because it promotes hygiene and health at site. | Done
[8 empty] | 2. Conduct Employee Survey to collect WASH-related data and any concerns with respect to WASH. |  | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No financial budget needed. | Impact on WASH services on Catchment Level impacting the hygiene facilities on catchment level. | Ensure betterment of WASH Services by working on the identified issues and communicating them with stakeholders. | Demonstrates GSK's commitment to environmental and social responsibility | This action provides Social, Environmental benefits because Improves sanitation and employee well-being. | Done
[8 empty] | 3. Collaborate with local governing bodies for improving current waste water facilties on catchment level. |  | 31st March 2026 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No financial budget needed. Site to explore with governmental bodies for upgradation of WWTP network. | Impact on Waste Water Disposal Facility direclty impacting WASH facilities on catchment level. | Check for fesability for upgrading waste water treatment facilities which will ensure better WASH Facility at Site. | Demonstrates GSK's commitment to environmental responsibility ensuring proper waste water facilities are present in the catchment. | This action provides Environmental, Economic benefits because it enhances water recycling and reduces waste. | In progress, Site to formally engage with KWSC by Q4 2025.
4 | Water Balance and Water Costs | Physical | No | A proper water balance is needed to manage water efficiently, understand water-related costs and trends. Not having a proper and updated water balance is likely to result in lost opportunity to optimise the water consumption and effectively meet GSK's water goals. | 3 | 3 | 9 | 1. Develop a water balance map using a scientific map by ensuring that all water inflows and outflows have been accounted for end-to-end including water usage in utilities. |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 10 Million needed for installation of auotamated water meters for ensuring better visibility of water usage. | Impact on Water Usage at Site leading to increased water consumption and increased costs | Prepare Water Balance and identify points that can be metered further. Ensure Project delivery by Q1 2026. | Identify key areas of inefficiency or water loss. | This action provides Economic, Environmental benefits because it improves water monitoring and management. | Done
[8 empty] | 2. Site should check for water losses and include the same in the water balance map. Formulate a plan to determine how these losses will be eliminated, wherever possible. |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Impact on Water Usage at Site leading to increased water consumption and increased costs | Identification of Water losses as per Water Balance | Identify key areas of inefficiency or water loss. | This action provides Economic, Environmental benefits because it jelps in reducing water wastage. | Done
[8 empty] | 3. Site to consider developing water balance map indicating variances. |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 10 Million needed for installation of auotamated water meters for ensuring better visibility of water usage and for seasonally updating data. | Impact on Water Usage at Site leading to increased water consumption and increased costs | Install Automated Flow Meters for better mapping of water balance and subsequent identification of water loss opportunities | Identify key areas of inefficiency or water loss. | This action provides Economic, Environmental benefits ss it enables accurate water usage tracking. | Done
[8 empty] | 4.Install more water meters that may be beneficial for effective measurement of water used on-site |  | 31st March 2026 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 10 Million needed for installation of auotamated water meters. | Impact on Water Usage at Site leading to increased water consumption and increased costs | Install Automated Flow Meters for better mapping of water balance and subsequent identification of water loss opportunities to reduce unaccounted water by 500 m3. | Identify key areas of inefficiency or water loss. | This action provides Economic, Environmental benefits as it enables accurate water usage tracking. | In progress, tracked through site regional sustainability meetings.
[8 empty] | 5. Site to include previously identified efficiency opportunities of Water Reuse/ Water Recycling identified via installation of water meters as part of its action plan. |  | 30th April 2026 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Site has identified oppourtunities to reduce water consumption and has identified projects against it. Details are as mentioned with each project. | Impact on Water Usage at Site leading to increased water consumption and increased costs | Water Related Projects to be added and tracked in monthly councils. Reduction in water consumption by 1000 m3 by 2024 year baseline. | Will help GSK in analysizing water challenges and take proactive measures | This action provides Economic, Environmental benefits as it reduces water loss and saves costs. | In progress, tracked through site regional sustainability meetings.
|  |  |  | Site should track its water costs closely and take it as an opportunity for continual improvement. Missing out on opportunities for optimization of water related costs, and savings. | 3 | 3 | 9 | 1. Site to track Water Related Costs including the Raw Water and Processing Costs. |  | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Increased Water Cost due to unavailability of water monitoring / cost tracking system | Tracking of Direct / Indirect Water Costs. | Will help GSK in analysizing water challenges related to costs and take proactive measures | This action provides Social, Economic benefits as it ensures accountability and progress tracking. | Done
5 | Extreme Weather and Incident Response | Physical + Reputational + Regulatory | Yes | Extreme weather conditions such as droughts or heavy rainfall may pose risk to business continuity, production loss, property damage, interruption to power supply damage to infrastructures, operational disruptions and compromise employee safety. Extreme weather (e.g., earthquakes, cyclones and droughts) may impact the supply chain and logistics which will disrupt raw material, finished good movement and lead to product shortages Opportunity for continual improvement. Without record of past incidents, Site will miss out on opportunities to improve its Incident Management System. | 2 | 3 | 6 | 1. Site to updated its Business Continuity Plan to cater for water shortage. Prioritize water uses which are crucial for the proper functioning of the Plant in the case of droughts or reduced water supply. |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Possible Loss of Production with site facing major water loss issue | Site BCP to be prepared to ensure site has proper mechanism that will be followed incase of any water availability scenario ensuring prioritization | Updating the BCP safeguards GSK's reputation and ensures consistent delivery of high-quality products to patients ensuring strategic water management with risk reduction. | This action provides Economic, Social benefits as it ensures operational continuity during water shortages. | Done
[8 empty] | 2. Site should develop dedicated storm water management plan. 3. Site should develop layout of pollution sources present on site. |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Risk that increased flow of storm water will result in site flooding | Ensure that there is no standing storm water at site and dedicated plan for storm water is prepared. | Helps preserve ecosystems by preventing stormwater pollution and strengthens GSK's reputation as an environmentally responsible organization | This action provides Environmental, Ecological benefits because it rrevents waterlogging and supports ecosystem health. | Done
[5 empty] | 2 | 3 | 6 | 4. Site to create mechanism for audit of chemical storage and containment areas, walkways and parking areas |  | 15th August 2025 | Done | Muhammad Bilal (Site EHS Lead) | Masood Khan (Site Director) | No Financial Budget needed. | Risk that site chemical sources will not be stored properly with risk of chemical spillage. | Ensure Chemical Storages are maintained appropriately and all findings of L2 Audits are catered for. | This initiative will help GSK safeguarding nearby ecosystems from contamination by proactively identifying and mitigating risks regarding storm water pollution. | This action provides Environmental, Social benefits because it prevents contamination and ensures safety. | Done
[8 empty] | 5. Conduct annual review of insurance coverage for all assets with possible damages due to extreme weather events. |  | 15th July 2025 | Done | Ibraheem Farhan (Site Finance Partner) | Masood Khan (Site Director) | No Financial Budget needed. | Risk that damage to site assets will not be catered in insurance coverage. | Ensure all site assets are insured properly. | This initiative will help GSK safeguard its assets ensuring all its assets are protected in case of an unforeseen event. | This action provides Economic benefits because Protects financial interests in case of damage. | Done
6 | On-site Water/ Wastewater and Stormwater Discharge | Physical + Reputational + Regulatory | No | Inadequate wastewater storage on-site might interrupt GSKs production if there is a disruption at on-site ETP for a prolonged period. Land application of treated wastewater has the potential to cause nearby groundwater and surface water pollution which would impact all stakeholders and may lead to compliance issues, show-cause notice from regulatory authorities. Biodiversity could also be impacted. This could result in a liability for the Plant. | 2 | 3 | 6 | 1. Site to ensure all Active Pharmaceutical Ingredients (API) from the wastewater are eliminated at the on-site ETP as per the EHAC Requirements. |  | 15th July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Risk that Site will discharge waste water containing hamrful API | Ensure that site water discharged is as per EHAC Requirements, | This initiative will help ensure GSK's commitment to sustainability and ensuring compliance to EHAC Standards. | This action provides Environmental, Ecological benefits because it maintains compliance and protects environment. | Done
[8 empty] | 2. Ensure that the treated wastewater quality, is in accordance with the requirements specified by SEPA. |  | 15th July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Risk that the treated waste water quality will not comply with local SEPA guidelines. | Ensure Trending of Treated Waste Water Perimeters in EHS Councils | This initiative will help ensure GSK's commitment to sustainability and ensuring compliance to EHAC Standards. | This action provides Environmental, Social benefits because it monitors water treatment effectiveness. | Done
[8 empty] | 3. Site should ensure all past incidents of accidental chemical spillage, oil spillage, wastewater discharge on-site or otherwise, if any, are documented. |  | 15th July 2025 | Done | Muhammad Bilal (Site EHS Lead) | Masood Khan (Site Director) | No Financial Budget needed. | Risk of that incidents related to chemical spillage will not be documented/ root cause not analyzed leading to more incidents in future | Ensure all incidents are documented on EHS One | This initiative will ensure that site can learn from all of its previous incidents. | This action provides Social, Environmental benefits because Improves transparency and safety. | Done
[8 empty] | 4. Conduct regualar maintenance of Water Treatment Facilities |  | 15th July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. Site has a dedicated inhouse utilities team for maintaining water treatment facilities. | Risk that water treatment facilities will not be maintained properly resulting in ETP Water spillage. | Ensure all water treatment facilities are maintained as per defined frequency on CMMS. | This initiative will help ensure GSK's commitment to sustainability and ensuring compliance to EHAC Standards. | This action provides Environmental, Economic benefits because it ensures operational efficiency and water quality. | Done
7 | Stakeholder Engagement | Reputational | No | Lack of engagement between the Site and the key stakeholders would result in the Site missing out on opportunities to proactively identify various water-related issues in the catchment | 3 | 3 | 9 | 1. Formulate a list of key stakeholders in the area |  | 1st July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses. | Collectively strengthen water quality/water balance initiatives on catchment level by sharing best practices. | Help interact with stakeholders and collectively work for ensuring sustainable water use in the catchment | This action provides Environmental, Ecological, Social benefits because it promotes sustainable water practices. | Done
[8 empty] | 2. Based on above list, Site should develop a formal Stakeholder Engagement Plan. |  | 15th July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses. | Collectively strengthen water quality/water balance initiatives on catchment level by sharing best practices. | Help interact with stakeholders and collectively work for ensuring sustainable water use in the catchment | This action provides Environmental, Ecological, Social benefits because it encourages supplier collaboration for water sustainability. | Done
[8 empty] | 3.Communicate with relevant stakeholders about activities taken up by Site/GSK for the greater good (e.g., water conservation measures). |  | 31st March 2026 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses. | Collectively strengthen water quality/water balance initiatives on catchment level by sharing best practices. | Help interact with stakeholders and collectively work for ensuring sustainable water use in the catchment | This action provides Social, Environmental benefits as it ensures continuous improvement in water practices. | In Progress
[8 empty] | 4. GSK has committed to ""Water neutrality by 2030 for all GSK Sites and key-suppliers located in water stressed regions"" implying taking collaborative actions to carry out water and sanitation education and infrastructure initiatives across the basin. Therefore, the Site with the help of GSK global may benefit from developing an engagement strategy with suppliers and understand their dependence on water along with any pertaining issues which they may have encountered related to their water use. |  | 2026-06-30 | Ongoing | Osama Muneer (Site Procurement Manager) | Masood Khan (Site Director) | No Financial Budget needed. | Water Level Depletion for suppliers leading to increased raw material cost for site. | Collectively strengthen water quality/water balance initiatives by engaging withv top suppliers and sharing best practices. | Help interact with suppliers and collectively work for ensuring sustainable water use in the catchment | This action provides Environmental, Economic benefits as it supports water conservation and cost savings. | In Progress
8 | Legal Requirements & Water Governance | Regualatory, Reputational | No | •As per the National Water Policy, industries are fifth in the list in terms of water allocation priorities. Thus, industries are likely to face water outages in the event of water shortages in the region. •Lack of collaboration between the government entities as well as the unavailability of allocated water and sewage infrastructure, are resulting in supply line damages, leading to water shortage in Karachi. | 4 | 1 | 4 | 1. Conduct periodic review of the documents and compliances of Site with respect to water and wastewater management. |  | N/A | Done | Muhammad Bilal (Site EHS Lead) | Masood Khan (Site Director) | No Financial Budget needed. | Risk that site will not meet compliance requirement of SEQS and SEPA. | Periodic Review Mechansim to be governed as part of EHS Counci. | Demonstrates GSK's commitment to environmental responsibility ensuring all relevant compliance requirements are met. | Environmental, Ecological, Social - Ensures compliance to all relevant legal/ regulatory requirements. | Done
9 | Indirect Water Use | Physical | No | Not understanding the water risks faced by suppliers and/or outsourced services may present a business continuity risk. Changes in supplier's water availability may disrupt the raw material and finished good movement and supply and lead to product shortages. | 2 | 3 | 6 | 1. Periodically monitor suppliers' response to water stewardship related actions and evaluate risks associated with decline in water availability/quality (e.g., does supplier have emergency response plans for water-related risks). Make this as a part of supplier management plan. |  | N/A | Done | Osama Muneer (Site Procurement Manager) | Masood Khan (Site Director) | No Financial Budget needed. | Water Level Depletion for suppliers leading to increased raw material cost for site. | Collectively strengthen water quality/water balance initiatives by engaging withv top suppliers and sharing best practices. | Help interact with suppliers and collectively work for ensuring sustainable water use in the catchment | Environmental, Ecological, Social - Encourages supplier collaboration for water sustainability. | Done
[8 empty] | 2. Engage with Water Service Providers for periodic monitoring of water consumption and tracking of projects. |  | 31st March 2026 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Water Level Depletion leading to increased costs of out sourced services | Collectively strengthen water quality/water balance initiatives on catchment level by sharing best practices. Reduce the water consumption of Swano Laundry by 500 US Gallons. | Help interact with stakeholders and collectively work for ensuring sustainable water use in the catchment | Social, Environmental - Ensures continuous improvement in water practices for service providers. | In Progress
[8 empty] | 3. Identify key suppliers to engage with to understand overall water footprint and explore water consumption reduction options. Interact with vendors and seek information on their water usage and risks. |  | 2026-06-30 | In Progress | Osama Muneer (Site Procurement Manager) | Masood Khan (Site Director) | No Financial Budget needed. | Water Level Depletion for suppliers leading to increased raw material cost for site. | Collectively strengthen water quality/water balance initiatives by engaging withv top suppliers and sharing best practices. | Help interact with suppliers and collectively work for ensuring sustainable water use in the catchment | Environmental, Economic - Supports water conservation and cost savings. | In Progress

## Action Status
Total Actions | 38
Completed | 28
In Progress/ On going | 10