## Revision (hidden)
Revision No. | Update Date | Update Context

## West Wharf
GSK Pakistan (West Wharf) Water Stewardship Action Plan
| Risks/Opportunities (in no particular order of importance) | Type(s) of Issue/Opportunity (physical, reputational, regulatory) | Shared Challenge in the Catchment? (Yes/No) | Context | Likelihood of Negative Impact Materializing (4-very likely, 3-likely, 2-unlikely, 1-very unlikely) | Potential Severity of Impact for Site (3-high/2-medium/1-low) | Potential Cost/ impact if Risk Materializing | Overall Risk Rating (will fill automatically once columns G and H are filled) | Site Planned action | Target | AWS Outcome Alignment | Lead (Owner) | Target Date | Status | Comments
1 | Water Availability | Physical + Reputational + Regulatory | Yes | ▪In Pakistan, per capita water availability is estimated to further decrease from 877 m3 in 2020 to 575 m3 in 2050 leading to water shortage ▪KWSB currently supplies 650 MGD (2954 MLD) of water against a demand of 820-1200 MGD, resulting in a shortfall of 155-535 MGD ~35% (232 MGD) of 650 MGD is lost during transmission due to aging infrastructure, decreasing the water availability to a mere 433 MGD (1968 MLD). ▪Progressive siltation is reported in Keenjhar Lake reducing its storage capacity. Water level has been continuously declining in the lake reaching 14.02 m. Water withdrawal from the lake will be disrupted if the levels go below 13.4 m. ▪The city's population is likely to grow by over 30 % from 2017 to 2030 and the water demand is likely to grow in the future. | 3 | 3 | 43877 cubic meters water loss per year | 9 | 1. Monitor water stress annually at the catchment level to take preparedness against anticipated risks (e.g., by engaging local authorities with access to such data). | Risk Mitigation |  | Abdullah | 2025-06-30 | Completed | -
[9 empty] | 2. Develop a reactive statement (regarding GSK's water stewardship) for use in case the Site is associated by external stakeholders to any water issue (e.g., water quality) with potential reputational impacts. | Reputational Risk mitigation |  | Hammad | 2025-06-30 | Completed | -
[9 empty] | 3. Update the Site's Business Continuity Plan (BCP) to cover all potential water-related issues (e.g., water availability; water quality; water costs; extreme weather events and their impact on infrastructure, availability, quality). | To ensure operational continuity |  | Hammad | 2025-07-31 | Completed | -
[9 empty] | 4. Explore alternate sources of water to minimize reliance on fresh (surface) water. 4.1.Undertake rainwater harvesting on-site to reuse harvested rainwater for productive use within the Site boundary and reduce the volume of freshwater sourced. | 45,210 gallons/yr water saving |  | Hammad | 2026-05-30 | In Progress | Piping system installed in PSC building. Placement for collection tank is under evaluation
[9 empty] | 5. Continue to identify opportunities to reduce / conserve water (conduct feasibility analysis for Water Generation through atmospheric water generator, as the Site is located in High humidity area). | 200/yr gallons of water saving |  | Hammad | 2025-06-30 | On Hold | Not feasable due to high cost and no ROI
|  |  |  | ▪KWSB's underperformance led to the promotion of water tankers in the region. The water hydrant operators have now evolved into a water mafia with powerful networks who are operating unregulated hydrants/illegally siphoning water from the main supply. With no KWSB water supply in many areas/households, dependency on water tankers have increased. Additionally, the water prices are also being hiked for the water tankers in Karachi affecting the low income population in the region. | 4 | 3 | 38,612,000 Rs/ year. The calculation was done assuming 4 Rs per gallon of water. Last years water consumption was taken. | 12 | 6. Conduct annual awareness training sessions on water stewardship and water conservation practices for Site employees. | To be achieve systematic approach fot assignment of training. |  | Hammad | 2025-10-15 | In Progress | Training pack has been developed. Assignment in Mylearning is pending
[9 empty] | 7. Make provision for adequate water storage facility in Site with capacity to provide backup for at least 3 days. | To ensure operational continuity |  | Hammad | 2025-06-30 | Completed | Assessment document is available
[9 empty] | 8. Track regulatory developments that may impact and/or pose risk to the Site with the concerned local authorities (e.g., KWSB, SEPA) by engaging with them on regular basis. Necessary basis to be determined by Site. | Building professional relation between govermental bodies. |  | Rayan | 2025-06-30 | Completed | Site in contact with SEPA quarterly for waste water discharge. Regulatory conversations also take place. Site records the conversations with all regulatory for audit purposes.
[9 empty] | 9a. Additionally, engage with industries, organizations, and / or government entities in the area to share information and best practices, discuss possible solutions and explore areas for collaboration that could benefit the local community(e.g., jointly develop water quality and WASH improvement programs for the upliftment of the catchment area; identify the potential source of contaminants in the surface water and drive clean-up activities; undertake rainwater harvesting and groundwater recharge projects at the watershed level to positively impact the water balance of the catchment and increase long-term sustainability of the watershed).". 9bThe site should follow the management plan as mentioned in the biodiversity study. | To ensure long term collaboration with stakeholders. |  | Ibrahim | 2025-06-30 | Completed | Refer to 3.1.1 and GSKs collaboration with WWF. All karachi sites are working together to improve catchment related best practices in terms of its quality and its cleaniness. These actions are integral part of their water stewardship plan which is tracked by the global team
2 | Water Quality | Physical + Reputational + Regulatory | Yes | Catchment Surface Water Quality KB Feeder Canal ▪Total coliform and E.coli contamination was found in the entirety of the canal indicating human and animal waste inflow ▪Kotri CETP (located the upstream (~41 km northeast) was reported to be non-functional and discharging untreated industrial waste and municipal waste directly into the canal. ▪Heavy metal contamination from fluoride and arsenic was also reported in the KB feeder canal. Keenjhar Lake ▪The water quality of Keenjhar Lake was well within the safe limits of National Environment Quality Standards (NEQS) except for the presence of bacterial contamination making it unfit for drinking purposes without treatment. No heavy metal contamination has been reported in Keenjhar Lake KWSB ▪According to KWSB, the NIPA hydrant receives water mainly from the K-II Filter Plant via the University Reservoir. However, the water quality reports for the K-II WTP were not available in the public domain and its compliance with the SSDWQ standard could not be ascertained. ▪It was reported that around 210 MGD of raw water in Karachi is supplied to the end user without any treatment due to the shortfall in the existing WTP capacities. ▪Considering that the Indus River, KB feeder Canal as well as Keenjhar Lake have been exhibiting bacterial pollution, the Site might be at risk of receiving bacterial-contaminated water. | 4 | 3 | US$120,000.00 - 200,000.00 for a new RO plus EDI plant. + Regulatory impact | 12 | 1. Develop a reactive statement highlighting GSK's commitment to water stewardship, to address potential reputational concerns in the event the Site is linked by external stakeholders to any water-related issue, such as water quality. | Reputational Risk mitigation |  | Tayyab | 2025-07-15 | Completed | -
[9 empty] | 1.The site should follow the stakeholder management plan as mentioned in AWS. Also, site should undertake a biodiversity study to support catchment water quality. | To ensure long term collaboration with stakeholders. |  | Abdullah | 2025-06-30 | Completed
|  |  |  | Site Quality ▪The Site performs drinking water quality analysis on a quarterly basis. ▪ Site monitors the incoming raw water quality for four parameters which includes TDS, pH, free chlorine and nitrate on a daily basis. | 2 | 2 | Regulatory Impact | 4 | 3. Site should include parameters like heavy metals and microbiological parameters in their list of water quality parameters for analysing the water received from water tankers. Currently, the Site performs analysis for four (04) parameters, respectively, which includes TDS, pH, free chlorine and nitrate and out sourced the testing for detail reports. The site should explore the feasibility to increase water testing frequency from third party. | Qulaity monitoring |  | Rayaan | 2025-10-31 | In Progress | A document to be made to check the feasibility for increasing the water testing frequency.
[9 empty] | 4. Undertake water risk assessment with the focus on water quality issues and to plan appropriate mitigation measures. | Risk Mitigation |  | Hammad | 2025-06-30 | Completed | Water risk assessment conducted
[9 empty] | 5. Conduct an adequacy check of the existing on-site water treatment plants. 5.1 Regularly clean and inspect the water storage tanks on-site to prevent microbial growth and contamination. | Create Well Maintenance Plan |  | Hammad | 2025-06-30 | Completed | The maintenance of water plant is periodically carried out as per maintenance management system.
3 | WASH | Physical + Reputational + Regulatory | Yes | ▪About 71% and 85% of the population in Pakistan have access to basic sanitation and basic hygiene status respectively as per the national estimates for 2023. ▪In Karachi, ~80% of the households have access to piped water, with private water tankers supplying much of the water required in informal settlements. However, Karachi's surface water as well as groundwater is reported to be heavily contaminated and thus requires prior treatment before catering to the residents of Karachi. According to the reports, 62% of the households receive water without any prior treatment which could give rise to water-borne diseases and affect human health. ▪Karachi has a separate system for the disposal of sewage and stormwater. However, it was reported that the stormwater drainage networks are not functioning due to massive encroachment and blockage resulting in stagnant water on the road. · Safe drinking water is available for all the users on-site. In West Wharf the site employees have access to filtered and bottled water while the other users have access to filtered water. · Additional hygiene products (such as soap, hand sanitizer, drying tools and, feminine hygiene product disposal facilities) are also available. · Site uses filtered water for drinking purposes | 3 | 2 | Health Impact + Regulatory impact | 6 | 1. Ensure proper access to WASH is provided at the Site. Periodic monitoring of WASH provided at Site and document the same. 1.1 Conduct awareness session for employees on WASH | To ensure good WASH practices at the site. |  | Rayan | 2025-06-30 | Completed | Maintenance of toilets and handwashing facilities is carried out on a daily basis. This includes cleaning of the toilets at multiple times throughout the day, and ensuring availability of soaps and drying tools for handwashing in all toilets. Training conducted on WASH (Kitchen Hygiene) for workers and action in J9 is in progress.
[9 empty] | 2. Conduct Employee Survey to collect WASH-related data and any concerns with respect to WASH during droughts/dry seasons. | To ensure good WASH practices at the site. |  | Saad | 2025-06-30 | Completed | WASH survey conducted
4 | Water Balance and Water Costs | Physical | No | ▪In updated water balance depicting the inflow, outflow and losses from different units may lead to missing out on opportunity to identify water conservation area and losses. | 3 | 3 | Operational inefficiency | 9 | 1. Develop a water balance map using a scientific map by ensuring that all water inflows and outflows have been accounted for end-to-end including water usage in utilities. This can be done via undertaking a formal water audit and accounting exercise (e.g.: excel based tool). | To save the water and optimize the process aiming at sustainable water balance |  | Syed Hammad khalid | 2025-06-30 | Completed
[9 empty] | 2. Site should check for water losses and include the same in the water balance map. Formulate a plan to determine how these losses will be eliminated, wherever possible. |  |  | Syed Hammad khalid | 2025-08-30 | Completed | Water losses are already being catered in site water balance. Actions (projects) are taken to incorporate these losses in the network
[9 empty] | 4. Identify additional areas in the Plant to install more water meters that may be beneficial for effective measurement of water used on-site (currently the Site has 14 No. of flow meters installed in the water line). 4.1 Invest in portable ultra-sonic meters to record smaller/more consistent flows for water maps. 4.2 Also, conduct regular maintenance and calibration of existing flow meters. |  |  | Syed Hammad khalid | 2025-09-30 | In Progress | Sourcing of additional flow meters in progress
[5 empty] | 3 | 3 | Water cost escalation | 9 | Annual review of water consumption at the site should be performed to assis its consumption in relevant areas | Operational sustainability |  | Syed Hammad khalid | 2025-06-30 | Completed
[9 empty] | 7. Site should maintain cost inventory with record of all water-related direct and indirect costs and track the same. This will help Site to deduce the true cost of water in its business and plan water-related projects with better understanding of return on investment (RoI). Develop an excel based tool to understand the trend in change in cost. [Example of water cost: In addition to cost incurred from procurement of water and treatment of water, costs should also include (but not limited to) items such as: payment for experts, fees and levies, data collection, technical studies, capital investments and depreciations, risk mitigation actions, stakeholder engagement activities, external communications and staffing, one time expenditure and recurring costs / operational expenses, and for ongoing monitoring, maintenance and management of water resources]. | To achieve operational sustainability by tracking cost of consumables in a site forum. |  | Syed Hammad khalid | 2025-06-30 | Completed
5 | Extreme Weather and Incident Response | Physical + Reputational + Regulatory | No | • Exposure of water-related infrastructure to natural disasters such as drought, riverine flood and extreme heat under current and future (due to climate change) scenarios may lead to damages and service interruptions as; ○ The area of Karachi West lies within a 'High' risk to water scarcity as per Think Hazard. ○ The area of Karachi West lies within 'Medium' risk to coastal flood as per Think Hazard. ○ The area of Karachi West lies within 'High' risk to extreme heat as per Think Hazard. ○ The area of Karachi West lies within 'High' risk to cyclone as per Think Hazard. ○ The area of Karachi West lies within 'Medium' risk to earthquake as per Think Hazard. • Past incidents of flood (latest in 2022) were found affecting Sindh province especially its agriculture sector. Heavy rainfall in monsoon than usual and melting glaciers caused the deadliest flood and it was described as the worst in the country's history causing at least 15 deaths in the Karachi city. There was almost 126 mm rainfall happened on July 11 along with clogged drains lead to inundate the business district. | 2 | 3 | Operational sustainability. | 6 | 1. Develop a crisis continuity plan to include: - Prioritize water uses which are crucial for the proper functioning of the Plant in the case of droughts or reduced water supply. | Risk Mitigation |  | Ibrahim | 2025-06-30 | Completed | Part of BCP
[9 empty] | 2. Site should develop/maintain dedicated storm water management plan and Stormwater Pollution Prevention Plan. | Prepare a layout for storm water management at the site. |  | Ibrahim | 2025-06-30 | Completed
|  |  |  | · Site has a dedicated Stormwater management Plan | 2 | 3 | Risk to the environment and the health of people across the site. | 6 | 3. Site to conduct an audit of chemical storage and containment areas, walkways and parking areas to identify any sources of stormwater contamination and take necessary measures to eradicate those sources. | Create maintenance plan for bund containments at the site. |  | Rayan | 2025-06-30 | Completed | L1 audits in place
[9 empty] | 4. Site should ensure all past incidents of accidental chemical spillage, oil spillage, wastewater discharge on-site or otherwise, if any, are documented along with photographs and videos. | To prepare a procure for incident reporting at the site. |  | Rayan | 2025-06-30 | Completed | This is already part of GSK Practice and stored in EHS One
| On-site Wastewater and Stormwater Discharge | Physical + Reputational + Regulatory | No | •A part of the treated wastewater is discharged via sewers to the Arabian Sea and the remainder was used in cooling towers and as supply for flash tanks •Site conducts analysis of treated wastewater for a total of seven (07) parameters via an external laboratory. All the parameters were found to be compliant with the SEQS discharge limits. |  |  |  |  | 2. Ensure that the treated wastewater quality is in accordance with the requirements specified by SEPA. | To comply with legal requirements |  | Rayan | 2025-06-15 | Completed
[9 empty] | 3.Site should evaluate the performance of the ETP plant and explore oppurtunities to upgrade the system as per new requirements |  |  | Ibrahim | 2025-12-30 | In Progress
[9 empty] | 5. Conduct performance evaluation of the wastewater treatment systems on-site on a regular basis | To comply with legal requirements |  | Tayyab | 2025-06-15 | Completed | Daily log books and weekly testing are performed and results are presented in EHS councils
7 | Stakeholder Engagement | Reputational | No | • Multiple stakeholders were identified for west wharf site. Site is continously putting efforts to maximize the stakeholder engagement and built a structured community to share water related issues and best practices. • West Wharf reported that they engage with the suppliers extensively. The activity undertaken with the supplier is not known. • West Wharf engages with SEPA for wastewater related issues | 2 | 2 | Operational sustainability | 4 | 1. Formulate a list of key stakeholders in the area | To ensure long term collaboration with stakeholders to drive AWS practices within a community. |  | Tayyab | 2025-06-15 | Completed
[9 empty] | 2. Based on above list, Site should develop a formal Stakeholder Engagement Plan and a dedicated team to monitor the situation and implement programs in the surrounding areas. Plan to include items such as engagement calendar/schedule, documentation of issues / challenges faced by the stakeholders, and actions planned. |  |  | Tayyab | 2025-06-30 | Completed
[9 empty] | 3. Drive all external water-related Corporate Social Responsibility (CSR) activities. Discuss water-related issues affecting the communities. |  |  | Tayyab | 2025-09-30 | In Progress
[9 empty] | 5.Communicate with relevant stakeholders about activities taken up by Site/GSK for the greater good (e.g., water conservation measures). |  |  | Tayyab | 2025-06-30 | Completed
[9 empty] | 6. GSK has committed to "Water neutrality by 2030 for all GSK Sites and key-suppliers located in water stressed regions" implying taking collaborative actions to carry out water and sanitation education and infrastructure initiatives across the basin. Therefore, the Site with the help of GSK global may benefit from developing an engagement strategy with suppliers and understand their dependence on water along with any pertaining issues which they may have encountered related to their water use. This will further benefit the Site to minimize any water risks encountered by its suppliers and to ensure business continuity/supply reliability to the Site. |  |  | Kaleem | 2025-06-30 | Completed
8 | Legal Requirements & Water Governance | Regulatory, reputational | Yes/No | •As per the National Water Policy, industries are fifth in the list in terms of water allocation priorities. Thus, industries are likely to face water outages in the event of water shortages in the region. •Lack of collaboration between the government entities as well as the unavailability of allocated water and sewage infrastructure, are resulting in supply line damages, leading to water shortage in Karachi. •KWSB promoted private tanker services to supply water to the city, which has now evolved into a water mafia with powerful networks operating unregulated hydrants across the city. •Water rates and distribution in Karachi are inequitable, with lower-income populations paying disproportionately more for less water consumption | 3 | 3 | Operational sustainability | 9 | 3. Conduct periodic review of the documents and compliances of Site with respect to water and wastewater management as per the contractual agreement / permits / regulatory codes. | To comply with legal requirements |  | Tayyab | 2025-06-30 | Completed | 1- Legal register that contains all relevant laws related to waste water managemnet is reviewed and updated on annual basis. 2- GSK implemented new tool, ENHESA, for regulatory compliance, whenever there is a change to regulatory requirements it indicates to the site.
[9 empty] | Partner with local stakeholders to share knowledge, address water-related challenges, and implement initiatives like WASH programs, contamination cleanup, and watershed projects to enhance sustainability and community well-being. | Risk Mitigation |  | Abdullah | 2025-06-30 | Completed
9 | Indirect Water Use | Physical | No | •Multiple raw material suppliers were identified within or close to the Lyari River catchment. As per WRI Aqueduct, the flood risk level and water stress for vendors were reported to be “Medium” and “High” respectively. Thus, these suppliers might face similar water risks as that of the Sites with respect to the catchment's water availability or quality. •Further, GSK has committed to "Water neutrality by 2030 for all GSK Sites and key-suppliers located in water stressed regions" implying taking collaborative actions to carry out water and sanitation education and infrastructure initiatives across the basin. | 2 | 3 | Operational sustainability | 6 | . Identify key suppliers to engage with to understand overall water footprint and explore water consumption reduction options. Interact with vendors and seek information on their water usage and risks. | To ensure long term collaboration with stakeholders to drive AWS practices within a community. |  | Saad/Tayyab | 2025-09-30 | In Progress
•Site has already approached all indirect service providers to receive their annual water consumption along with their water related challenges. A meeting is planned in august with the relevant stakeholders to inform them about GSKs ambition to pursue AWS certification and to understand their water related challenges.
[9 empty] | Engage with the suppliers located within the catchment to identify water related risks, and develop a joint action plan to address common water related risks |  |  | Saad/Tayyab | 2025-09-30 | In Progress
Likelihood
4
3
2
[8 empty] | 1 |  |  | very likely
likely
unlikely
very unlikely