## Revision (hidden)
Revision No. | Update Date | Update Context

## Sheet1 (hidden)
Water Availability
Water Quality
WASH
Water Balance and Water Costs
Extreme Weather and Incident Response
On-site Wastewater and Stormwater Discharge
Stakeholder Engagement
Legal Requirements & Water Governance
Indirect Water Use

## Korangi
GSK Pakistan (Korangi) Water Stewardship Action Plan
| Issue/Opportunities (in no particular order of importance) | Type(s) of Issue/Opportunity (physical, reputational, regulatory) | Shared Challenge in the Catchment? (Yes/No) | Description of Potential Negative Impact(s) on Site / Catchment | Likelihood of Negative Impact Materializing (4-very likely, 3-likely, 2-unlikely, 1-very unlikely) | Potential Severity of Impact for Site (3-high/2-medium/1-low) | Overall Risk Rating (will fill automatically once columns G and H are filled) | Site Action | AWS Outcome Alignment | Action | Lead Associate | Budget | Target completion date | Progress Check (date and status) | Action | Action Status | Lead (Owner) | Target Date | Target completion date | Progress Check (date and status) | Responsible Person | Accountable Person | Financial Budget Allocation | Business Impact if the Risk Materializes
1 | Water Availability | Physical + Reputational + Regulatory | Yes | Continuous depletion in the groundwater level might result in Site not meeting its water requirements. This poses a threat to Site’s water availability which would impact operations resulting in loss of business. Irregularities in raw material supply by suppliers (facing water challenges) which are in the same catchment of Site. Lack of adequate water may also impact the Site biodiversity. Inadequate water supply may compromise access to WASH for employees and communities. | 4 | 3 | 12 | 1. Monitor water stress annually at the catchment level to take preparedness against anticipated risks (e.g., by engaging local authorities with access to such data). |  | 1. Site to co-ordinate with SEPA and WWF to get catchment related data. | Abdullah Sagheer | N/A | 15th August 2025 | Done | Site to co-ordinate with SEPA and WWF to get catchment related data. | Co-ordinate with SEPA / WWF to get catchment related data. | Abdullah | 2025-06-30 | 31st December 2025 | In Progress | Abdullah Sagheer (Water Project Manager) | Masood Khan (Site Director) | No Financial Budget needed. GSK has entered in a mutti-million dollar partnership with WWF where WWF will be conducting surveys on catchment level to get ground water level and quality data. | Possible Loss of Production with volume reduction incase site doesn’t plan accordingly for depleting water levels.
[8 empty] | 2. Update the Site's Business Continuity Plan (BCP) to cover all potential water-related issues |  | Site Crisis and Continuity Management to be updated to include clause for Water Shortage. | Muhammad Ubaid | N/A | 15th August 2025 | Done |  |  |  |  | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | In case the Risk of Water Shortage Materailizes, Site will not have a proper plan for dealing with the risk.
[16 empty] | Site BCP to be updated | Umar Yazdani / Aftab | 2025-06-30
[8 empty] | 3.Check Feasability rainwater harvesting on-site to reuse harvested rainwater for productive use within the Site boundary and reduce the volume of freshwater sourced. 3.1 Identify authorized third-party private tanker suppliers and establish supply during drought situations. |  | 1. Feasibility needs to be assessed for rain harvesting as not much rainfall in Karachi 2. Ensure Contract with Tanker Water Service Provider and include exclusivity part. | Muhammad Ubaid | N/A | 5th August 2025 | Done |  | Rain Water Harvesting Pilot Project already in place and part of waterfall (Ceph Rooftop). Exclusivity part added in ghulam Nabi's latest contract | Umar Yazdani | Completed | 5th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 3.5 Million is allocated for pilot project of rain water harversting | Incase the ground wate level depletes, site will not be able to rely on tanker water as well for backup supply leading to production losses.
[8 empty] | 4. Continue to identify opportunities to reduce / conserve water (e.g. installation of recovery plant for RO reject water) |  | Site to identify water conservation projects to reduce/reuse/conserve water. | Muhammad Ubaid | N/A | 1st August 2025 | Done |  | Water Waterfall is built with identifed projects and their timelines and tracked in monthly energy/water calls. | Umar Yazdani | Completed | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Site has identified oppourtunities to reduce water consumption and has identified projects against it. Details are as mentioned with each project. | Increased Water Consumption with more reliance on water tankers leading to increased costs.
|  |  |  | Steadily declining ground water resources may encourage the regulators to implement stringent regulations/ limitations on industrial water use, which may impact Sites water supply and increase overall water costs. | 4 | 3 | 12 | 5. Conduct annual awareness training session on water stewardship and water conservation practices for all Site employees. |  | Site to provide training to Employees via My Learning | Muhammad Ubaid | N/A | 1st August 2025 | Done |  | AWS Presentation to be made and assigned to every individual onsite via My Learning Curricula | Umar Yazdani | 2025-06-15 | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Site employees will not be familiar with Water conservation practices leading to increased water consumption due to behavioral issues leading to increased water costs.
[8 empty] | 6. Site to assess the Current Water Storage Capacity and check feasability for Water Storage Capacity Increase. |  | Site to assess the Current Water Storage Capacity and check feasability for Water Storage Capacity Increase. | Muhammad Ubaid | N/A | 1st July 2025 | Done | Needs to assess the commercial feasibility as it requires major capital investment | Review to be prepared for current storage capacity with reference to continous supply from bores, critical spares maintained for RO Plant and Bore Wells. | Umar Yazdani | Completed | 1st July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 10 Milllion will be required incase Site requires to increase its water capacity. | In case of water unavailability and lack of storage, site not be able to cater for prodcution volume due to lack of capacity.
[8 empty] | 7. Site to engage with Stakeholders for sharing of information and best practices |  | Site to engagement with Stakeholders for sharing of information and best practices | Muhammad Ubaid | N/A | 25th August 2025 | In Progress | ERM has shared Stakeholder Engagement materials | Stakeholders in Same Catchment to be enaged with. Site has engaged with Nestle and have meeting plans with 6 other stakeholders by 25th June 2025. | Umar Yazdani | 2025-06-30 | 31st December 2025 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses.
[8 empty] | 8. Site to assess commercial feasability for installation of piezometers for monitoring ground water level 8 8.1 Site to assess feasability for installation of additional borewell. |  | 1. Site to assess commercial feasability for installation of piezometers for monitoring ground water level 2. Site to assess feasability for installation of additional borewell. | Muhammad Ubaid | N/A | 1st August 2025 | Done | Needs to assess the commercial feasibility as it requires major capital investment | 1. Annual Hydrogeological study is performed by site to monitor catchment water level. (Evidence Attached) 2. Site in process of assessing commercial feasability of installing piezometers. Quotes obtained (Review Performed) 3. Additional Borewell on site is also initiated and in procurement / technical evaluation stage. Ask for data from WWF as well. | Umar Yazdani | Completed | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 3 Million is estimated for piezometer installation while budget of over 80 Million will be required for new borewell. | Possible Loss of Production with volume reduction incase site doesn’t plan accordingly for depleting water levels of the current bores.
| Water Quality |  |  | Site might have to invest in better equipment, filters, and chemicals which might increase the cost to operate the water purification systems in the plant. Low water quality may trigger regulatory risks such as more stringent water regulations being imposed in the region. Also, health risks to the Plants' water and the nearby community (Site provides drinking water to the nearby community) cannot be ruled out Poor water quality may also result in an impact on the nearby communities as well as IWRA's and imply a potential reputational risk for the industries operating in the area as a possible association with poorly performing industrial users. Poor water quality may impact product quality and brand reputation | 4 | 3 | 12 | 1. Site to engage with stakeholders for share informmation, best practices and possible areas of collaboration. |  | 2. Site to engage with stakeholders for share informmation, best practices and possible areas of collaboration. | Muhammad Ubaid | N/A | 25th August 2025 | In Progress |  | As mentioned in R12. | Umar Yazdani | 2025-06-30 | 31st December 2025 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses.
|  |  |  | The Site is dependent on the groundwater for all of its operations. In case of any quality issue, the operations will be affected until alternative sources are found. Further, Site might also have to increase the frequency of monitoring water on-site for comprehensive suite of analytes. | 2 | 2 | 4 | 3. Site to include important parameters in contract for Tanker Water Provider and test for the same. 3.1 Site to treat water from tap (accessed by the community) for comprehensive suite of analytes as mentioned in the NSDWQ/SSDWQ |  | 3. Site to include important parameters in contract for Tanker Water Provider and test for the same. 3.1 Site to treat water from tap (accessed by the community) for comprehensive suite of analytes as mentioned in the NSDWQ/SSDWQ | Muhammad Ubaid |  | 15th August 2025 | Done | Tap water is already treated to meet the parameters of SSDWQ. Annual testing is in place | Site's Main Source of Water are Bore Wells which are being tested monthly as per SSDWQ Guidelines. All Water on Site is treated via the Main RO Plant (utility water and tap water) before being utilized further. TAP Water is being tested on annual basis by external third party. Note: Procedural update: if any deviation observed in groundwater, tap water to be assessed. | Umar Yazdani | Completed | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Risk of impact on product quality incase the tanker water is not as per requirement. Also incase the drinking water is not as per requirement of SSDWQ, employee health will be impacted leading to more on job sickness leaves impacting site operations .
[8 empty] | 4.Adjust the testing frequency of borewell water (monthly or quarterly basis) for a comprehensive suite of analytes (SSDWQ), as deemed necessary, based on the observed trends in water quality. |  | 4.Adjust the testing frequency of borewell water (monthly or quarterly basis) for a comprehensive suite of analytes (SSDWQ), as deemed necessary, based on the observed trends in water quality. | Muhammad Ubaid |  | 15th August 2025 | Done |  | Monthly Testing of Bore Wells (Bore 1 and Bore 2) done. | Umar Yazdani | Completed | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 500,000 needed for bore water testing. | In case the bore water quality depletes, site will have to find corrective solution to ensure that site Reverse Osmosis Plant is operational. In case the RO Plant shuts down, complete site operations will be hampered.
[8 empty] | 5. Regularly clean and inspect the water storage tanks on-site to prevent microbial growth and contamination. |  | 5. Regularly clean and inspect the water storage tanks on-site to prevent microbial growth and contamination. | Muhammad Ubaid |  | 15th August 2025 | Done |  | Adequacy check to be conducted in Q2 2025 water storage tanks are cleaned on annual basis as per CMMS. | Umar Yazdani | 2025-06-30 | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No financial budget needed. Site performs inhouse maintenance and inspection of water storage tanks. | Impact on Stored Water Quality incase of microbial growth in water storage tanks impacting site operations.
3 | WASH | Physical + Reputational + Regulatory | Yes | Poor access to WASH amenities at the catchment might impact the health of the Site's employees, Contractual staff, and other stakeholders related to the Site. This can affect the productivity of the employees, make them vulnerable to diseases. Inadequate WASH conditions can deteriorate the quality of the surface water and impact the communities relying on that water source. | 3 | 2 | 6 | 1. Ensure proper access to WASH is provided at the Site. 1.1 Conduct awareness session for employees on WASH. |  | 1. Ensure proper access to WASH is provided at the Site. 1.1 Conduct awareness session for employees on WASH. | Muhammad Ubaid | N/A | 10th August 2025 | Done |  | Proper access to WASH is ensured at site and is maintained. Awareness sesion to be conducted at each site respectively on WASH. Pictorial and training record to be submitted as evidence | Umar Yazdani | 2025-06-30 | 10th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No financial budget needed.
[8 empty] | 2. Conduct Employee Survey to collect WASH-related data and any concerns with respect to WASH during droughts/dry seasons. |  | 2. Conduct Employee Survey to collect WASH-related data and any concerns with respect to WASH during droughts/dry seasons. | Muhammad Ubaid | N/A | 25th August 2025 | In Progress |  | Hard copy survey to be conducted for all employees related to WASH data | Umar Yazdani | 2025-06-30 | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No financial budget needed.
[8 empty] | 3. Collaborate with local governing bodies for feasability of waste water treatment facility upgradation at catchment level. |  | 3. Collaborate with local governing bodies for feasability of waste water treatment facility upgradation. | Muhammad Ubaid | N/A |  |  | Needs to assess the feasibility | Feasability to be assessed. Meeting to be arranged with KWSB for this activity. | Umar Yazdani | 2025-06-30 | 31st December 2025 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No financial budget needed. Site to explore with governmental bodies for upgradation of WWTP network.
4 | Water Balance and Water Costs | Physical | No | A proper water balance is needed to manage water efficiently, understand water-related costs and trends. Not having a proper and updated water balance is likely to result in lost opportunity to optimise the water consumption and effectively meet GSK's water goals. | 3 | 3 | 9 | 1. Develop a water balance map using a scientific map by ensuring that all water inflows and outflows have been accounted for end-to-end including water usage in utilities. |  | 1. Develop a water balance map using a scientific map by ensuring that all water inflows and outflows have been accounted for end-to-end including water usage in utilities. |  |  |  |  | Site has installed 24 flow metres. Site will improve the current water balance based on the new flow metre readings | Site has made draft water balance as per Nashik Template. Once finalized and reviewed by ERM, will get it second reviewed by third party as well. Water balance to be shared to ERM. | Umar Yazdani | 2025-06-30 | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 10 Million needed for installation of auotamated water meters for ensuring better visibility of water usage.
[8 empty] | 2. Site should check for water losses and include the same in the water balance map. Formulate a plan to determine how these losses will be eliminated, wherever possible. | [7 empty] | Once Water Balance is finalized, Water Losses elimination plan will be made | Umar Yazdani | 2025-06-30 | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed.
[8 empty] | 3. Site to consider developing separate water balance maps for indicating high and low variances 3.1 Continue periodically reviewing and updating Site water balance map as per current water log data, process changes, other changes affecting the map. |  | 2. Periodically Review and Update | [5 empty] | Water Balance will be prepared for two seasons (summer and winter) Water Balance regularly updated during any new improvement | Umar Yazdani | 2025-06-30 | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 10 Million needed for installation of auotamated water meters for ensuring better visibility of water usage and for seasonally updating data.
[8 empty] | 4. Identify additional areas in the Plant to install more water meters that may be beneficial for effective measurement of water used on-site |  | Need to assess the commercial feasibility |  |  |  |  | Need to assess the commercial feasibility | Flow Meters are installed at inlet and Outlet of ETP. Site also has a portable ultra sonic meter for flow monitoring. Site in Progress of Wave 2 Metering by August 2025. Project approval currently under progress. | Umar Yazdani | Completed | 15th July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Financial Budget of Rs 10 Million needed for installation of auotamated water meters.
[8 empty] | 5. Site to include previously identified efficiency opportunities of Water Reuse/ Water Recycling in the Action Plan. |  | Plan is place |  |  |  |  | Plan is place | Action Plan is in place and regulary being discussed in monthly calls. | Umar Yazdani | Completed | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | Site has identified oppourtunities to reduce water consumption and has identified projects against it. Details are as mentioned with each project.
|  |  |  | Site should track its water costs closely and take it as an opportunity for continual improvement. Missing out on opportunities for optimization of water related costs, and savings. | 3 | 3 | 9 | 1. Site to track Water Related Costs including the Raw Water and Processing Costs. | [7 empty] | As Mentioned in R6. | Umar Yazdani | 2025-06-30 | 1st August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed.
5 | Extreme Weather and Incident Response | Physical + Reputational + Regulatory | Yes | Extreme weather conditions such as droughts or heavy rainfall may pose risk to business continuity, production loss, property damage, interruption to power supply damage to infrastructures, operational disruptions and compromise employee safety. Extreme weather (e.g., earthquakes, cyclones and droughts) may impact the supply chain and logistics which will disrupt raw material, finished good movement and lead to product shortages Opportunity for continual improvement. Without record of past incidents, Site will miss out on opportunities to improve its Incident Management System. | 2 | 3 | 6 | 1. Site to updated its Business Continuity Plan to cater for water shortage. Prioritize water uses which are crucial for the proper functioning of the Plant in the case of droughts or reduced water supply. | [7 empty] | As mentioned in R6 | Umar Yazdani | 2025-06-30 | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed.
[8 empty] | 2. Site should develop dedicated storm water management plan. 3. Site should develop layout of pollution sources present on site. |  | Needs to assess the commercial feasibility as it requires major capital investment |  |  |  |  | Needs to assess the commercial feasibility as it requires major capital investment | Site to prepare Storm Water Management and Storm Water Pollution Prevention Plan with EHS. (SOP's are already in place and in use) | Umar Yazdani / Bilal | 2025-06-30 | 15th August 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed.
[5 empty] | 2 | 3 | 6 | 4. Site to create mechanism for audit of chemical storage and containment areas, walkways and parking areas |  | All chemical storage areas have bunds around them |  |  |  |  | All chemical storage areas have bunds around them | Chemical Storage Area audit part of EHS L1 Inspection Plan. Walkways / Parking areas to be covered in Storm Water Managemement Plan | Umar Yazdani / Bilal | Completed | 15th August 2025 | Done | Muhammad Bilal (Site EHS Lead) | Masood Khan (Site Director) | No Financial Budget needed.
[8 empty] | 5. Conduct annual review of insurance coverage for all assets with possible damages due to extreme weather events. | [7 empty] | Insurance Coverage for all assets is done. Documentation to be obtained from Finance and will be shared with ERM for Review. | Umar Yazdani / Ibraheem | Completed | 15th July 2025 | Done | Ibraheem Farhan (Site Finance Partner) | Masood Khan (Site Director) | No Financial Budget needed.
6 | On-site Wastewater and Stormwater Discharge | Physical + Reputational + Regulatory | No | Inadequate wastewater storage on-site might interrupt GSKs production if there is a disruption at on-site ETP for a prolonged period. Land application of treated wastewater has the potential to cause nearby groundwater and surface water pollution which would impact all stakeholders and may lead to compliance issues, show-cause notice from regulatory authorities. Biodiversity could also be impacted. This could result in a liability for the Plant. | 2 | 3 | 6 | 1. Site to test and eliminate Active Pharmaceutical Ingredients (API) from the wastewater at the on-site ETP. |  | PiE calculation is in place. All discharges are within EHAC limits |  |  |  |  | PiE calculation is in place. All discharges are within EHAC limits | PIE Calculation is in place and it is updated whenever any changes made to waste water supply. All discharges are within EHAC Limits Note: BSI accredition non applicable. | Umar Yazdani / Bilal | Completed | 15th July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed.
[8 empty] | 2. Ensure that the treated wastewater quality, is in accordance with the requirements specified by SEPA. | [7 empty] | Waste Water Sampliing + Testing Done on Quartetly Basis. Testing Reports part of EHS L2 Audit and are within SEQS limits. | Umar Yazdani / Bilal | Completed | 15th July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed.
[8 empty] | 3. Site should ensure all past incidents of accidental chemical spillage, oil spillage, wastewater discharge on-site or otherwise, if any, are documented. | [7 empty] | As mentioned in R33 and R34 | Umar Yazdani | Completed | 15th July 2025 | Done | Muhammad Bilal (Site EHS Lead) | Masood Khan (Site Director) | No Financial Budget needed.
[8 empty] | 4. Conduct regualar maintenance of Water Treatment Facilities | [7 empty] | Yes, performance evaluation is conducted by recording and reviewing the data of effluent parameters. Is this evidence enough? | Umar Yazdani | Completed | 15th July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. Site has a dedicated inhouse utilities team for maintaining water treatment facilities.
7 | Stakeholder Engagement | Reputational | No | Lack of engagement between the Site and the key stakeholders would result in the Site missing out on opportunities to proactively identify various water-related issues in the catchment | 3 | 3 | 9 | 1. Formulate a list of key stakeholders in the area |  | ERM has provided the list of stakeholders and the contact details for Sindh Environmental Protection Agency (SEPA) and WWF Pakistan. No contact information was available for KWSB |  |  |  |  | ERM has provided the list of stakeholders and the contact details for Sindh Environmental Protection Agency (SEPA) and WWF Pakistan. No contact information was available for KWSB | Stakeholder Engagement Sheet has been prepared. | Umar Yazdani | Completed | 1st July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses.
[8 empty] | 2. Based on above list, Site should develop a formal Stakeholder Engagement Plan. |  | Needs to develop framework |  |  |  |  | Needs to develop framework | Stakeholder Engagement Sheet has been prepared. Team is there for Stakeholder Engagement Plan Implementation and Monitoring. | Umar Yazdani | 2025-06-30 | 15th July 2025 | Done | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses.
[8 empty] | 3.Communicate with relevant stakeholders about activities taken up by Site/GSK for the greater good (e.g., water conservation measures). |  | Needs to develop framework |  |  |  |  | Needs to develop framework | Local Government bodies part of stakeholder engagement plan to be engaged with, | Umar Yazdani | 2025-06-30 | 31st December 2025 | In Progress | Muhammad Ubaid (FLP-Engineering) | Masood Khan (Site Director) | No Financial Budget needed. | Ground Water level depletion leading to unavailability of ground water and further reliance on tanker water leading to increased costs. May also lead to lack of water supply leading to production losses.
[8 empty] | 4. GSK has committed to ""Water neutrality by 2030 for all GSK Sites and key-suppliers located in water stressed regions"" implying taking collaborative actions to carry out water and sanitation education and infrastructure initiatives across the basin. Therefore, the Site with the help of GSK global may benefit from developing an engagement strategy with suppliers and understand their dependence on water along with any pertaining issues which they may have encountered related to their water use. This will further benefit the Site to minimize any water risks encountered by its suppliers and to ensure business continuity/supply reliability to the Site. |  | Needs to develop framework |  |  |  |  | Needs to develop framework | Site is in partnership with WWF for strategic improvements across the Sutlej Basin. Supplier Water Stewardship Program is in progress. | Osama Muneer / Abdullah | 2025-07-15 | 31st December 2025 | Ongoing | Osama Muneer (Site Procurement Manager) | Masood Khan (Site Director) | No Financial Budget needed.
8 | Legal Requirements & Water Governance | Regualatory, Reputational | No | •As per the National Water Policy, industries are fifth in the list in terms of water allocation priorities. Thus, industries are likely to face water outages in the event of water shortages in the region. •Lack of collaboration between the government entities as well as the unavailability of allocated water and sewage infrastructure, are resulting in supply line damages, leading to water shortage in Karachi. |  |  |  | 1. Conduct periodic review of the documents and compliances of Site with respect to water and wastewater management. | [7 empty] | Site has contracs with Ghuklam Nabi Agreement valif for 18 Months. EHS Legal Register has all relevant documents pertaining to water and waste water management and are reviewed on annual basis | Umar Yazdani |  | N/A | Done | Muhammad Bilal (Site EHS Lead) | Masood Khan (Site Director) | No Financial Budget needed.
[8 empty] | 2. Track regulatory developments that may impact and/or pose risk to the Site with the concerned local authorities (e.g., KWSB, SEPA) by engaging with them on an annual basis. | [7 empty] | In Progress | Umar Yazdani | 2025-07-15 | N/A | Done | Muhammad Bilal (Site EHS Lead) | Masood Khan (Site Director) | No Financial Budget needed.
9 | Indirect Water Use | Physical | No | Not understanding the water risks faced by suppliers and/or outsourced services may present a business continuity risk. Changes in supplier's water availability may disrupt the raw material and finished good movement and supply and lead to product shortages. | 2 | 3 | 6 | 1. Periodically monitor suppliers' response to water stewardship related actions and evaluate risks associated with decline in water availability/quality (e.g., does supplier have emergency response plans for water-related risks). Make this as a part of supplier management plan. |  | Needs to develop framework |  |  |  |  | Needs to develop framework | Site is in partnership with WWF for strategic improvements across the Sutlej Basin. Supplier Water Stewardship Program is in progress. | Osama Muneer/ Abdullah Sagheer | 2025-07-15 | N/A | Done | Osama Muneer (Site Procurement Manager) | Masood Khan (Site Director) | No Financial Budget needed.
[8 empty] | 2. Identify key suppliers to engage with to understand overall water footprint and explore water consumption reduction options. Interact with vendors and seek information on their water usage and risks. |  | Needs to develop framework Raw material suppliers mapped in 1.4.1 of OneNote. |  |  |  |  | Needs to develop framework Raw material suppliers mapped in 1.4.1 of OneNote. | Osama to confirm if any suppliers are in catchment, engagement to be done accordingly | Osama Muneer/ Abdullah Sagheer | 2025-07-15 | 31st December 2025 | In Progress | Osama Muneer (Site Procurement Manager) | Masood Khan (Site Director) | No Financial Budget needed.