## Revision
Revision No. | Update Date | Update Context
1 | 2025-06-25 | 1st Version

## Sheet1 (hidden)
Water Availability
Water Quality
WASH
Water Balance and Water Costs
Extreme Weather and Incident Response
On-site Wastewater and Stormwater Discharge
Stakeholder Engagement
Legal Requirements & Water Governance
Indirect Water Use

## F-268
GSK Pakistan (F-268) Water Stewardship Action Plan
S.No | Issue/Opportunities (in no particular order of importance) | Type(s) of Issue/Opportunity (physical, reputational, regulatory) | Shared Challenge in the Catchment? (Yes/No) | Description of Potential Negative Impact(s) on Site's / Catchment | Likelihood of Negative Impact Materializing (4-very likely, 3-likely, 2-unlikely, 1-very unlikely) | Potential Severity of Impact for Site (3-high/2-medium/1-low) | Overall Risk Rating (will fill automatically once columns G and H are filled) | Site Action | AWS Outcome Alignment | Target completion date | Progress Check (date and status) | Responsible Person | Accountable Person | Objective | Target | Achievement | Value creation | Status/Comments
1 | Water Availability | Physical + Reputational + Regulatory | Yes | Continuous depletion in the groundwater level might result in Site not meeting its water requirements. This poses a threat to Site’s water availability which would impact operations resulting in loss of business. Irregularities in raw material supply by suppliers (facing water challenges) which are in the same catchment of Site. Lack of adequate water may also impact the Site biodiversity. Inadequate water supply may compromise access to WASH for employees and communities. | 4 | 3 | 12 | 1. Plan Monitor water stress annually at the catchment level to take preparedness against anticipated risks (e.g., by engaging local authorities with access to such data). |  | 2025-12-01 | In Progress | Abdullah Sagheer (Water Project Manager) | Khurshand Iqbal (Site Director) | To receive latest updates of water challenges at the catchment level | To esclate the SLT about the recent on going developments at catchment level & escalate if any geopolitical tension appears | N/A | Will help GSK in analysizing water challenges and take proactive measures | In Progress
[8 empty] | 1.1. Biodiversity assessment to be conducted of the Keenjhar Lake |  | 2025-12-01 | In Progress | Abdullah Sagheer (Water Project Manager) | Khurshand Iqbal (Site Director) | To set a base line for Keenjhar interms of biodiversity & Water Quality | Completed Biodiversity Report | Future intervention Support | Will help GSK being responsible company in the society for analysizing water challenges and take proactive measures | In Progress
[8 empty] | 2. Water Stewardship to be made part of EHS Council Agenda |  | 2026-01-01 | In Progress | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To take proactive measures for any water associated challenges | To seek help from the production floor for future Projects identification and seek water wastages (If any) | Future Projects identification | Will help GSK in analysizing water challenges and take proactive measures | In Progress
[8 empty] | 3.Check Feasability rainwater harvesting on-site to reuse harvested rainwater for productive use within the Site boundary and reduce the volume of freshwater sourced. |  | 2027-01-01 | In Progress | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | Extracting potential source of rain water | Reducing Water Footprints Target Savings: 1050 m³ Timeline: Jan-2027 (Phase # 2) | N/A | Will help in achieving water waterfall targets as part of sustainability initiative from GSK Regional Team | In Progress Project ID: 7500PK-IM-25052
[8 empty] | 5. Conduct annual awareness training session on water stewardship and water conservation practices for all employees. |  | 2025-11-01 | In Progress |  | Khurshand Iqbal (Site Director) | Achieving water waterfall Regional Sustainability Targets | Reducing Water Footprints | N/A (Journey Goes-On) | Will help in achieving water waterfall targets as part of sustainability initiative from GSK Regional Team | In Progress
|  |  |  | Steadily declining ground water resources may encourage the regulators to implement stringent regulations/ limitations on industrial water use, which may impact Sites water supply and increase overall water costs. | 4 | 3 | 12 | 6. Site to assess the Current Water Storage Capacity and check feasability for Water Storage Capacity Increase. |  | 2025-12-01 | In Progress | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To tackle forecasted future challenges (If any) | Increasing Site Storage Capacity (Along with Rain Water Harvasting) Approximate Savings: 1050 m3 (Phase # 2) Timeline: Jan-2027 | N/A | Helping GSK to tackle operations in case of water scarcity | In Progress Project ID: 7500PK-IM-25052 Approximate Savings: 1050 m³
[8 empty] | 7. Site to further explore best practice in the catchment |  | 2025-08-25 | Done | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | GSK Employees as responsible citizen to educate the community for any water challenges | Motivating catchment to achieve comon goals of reducing water footprints | N/A | Responsible Water Utilization & Project identification from the community | Done
2 | Water Quality | Physical + Reputational + Regulatory | Yes | Potential contaminated water towards causing increased Algae & Microbial count | 3 | 2 | 6 | 5. Regularly clean and inspect the water storage tanks on-site to prevent microbial growth and contamination on CMMs |  | 2025-12-01 | In Progress | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To inspect the tank internal health of tank and seek any abnormality | Annual Based Tank Inspection | N/A | N/A | In Progress
3 | WASH | Physical + Reputational + Regulatory | Yes | Poor access to WASH amenities at the catchment might impact the health of the Site's employees, Contractual staff, and other stakeholders related to the Site. This can affect the productivity of the employees, make them vulnerable to diseases. Inadequate WASH conditions can deteriorate the quality of the surface water and impact the communities relying on that water source. | 3 | 2 | 6 | 1. Sufficiency Assessment to be made for wash services at site 2. Ensure proper access to WASH is provided at the Site. |  | 2025-12-01 | In Progress | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To ensure proper access to Water, Sanitation, and Hygiene (WASH) facilities at the site and build awareness among employees about the importance of maintaining hygiene and sanitation practices | Provide access to adequate WASH infrastructure (clean drinking water, functional sanitation facilities, and hygiene stations) for 100% of employees at the site. | Installed/Upgraded WASH facilities, including clean drinking water points, handwashing stations, and sanitation areas. | Improved employee health and well-being by reducing risks associated with poor hygiene and sanitation. Enhanced productivity and morale by fostering a safer, cleaner, and more hygienic working environment. Demonstrated GSK’s commitment to sustainability and employee welfare, aligning with corporate responsibility goals. | In Progress
[8 empty] | 2. Conduct Employee Survey to collect WASH-related data and any concerns with respect to WASH during droughts/dry seasons. |  | 2025-12-01 | In Progress |  | Khurshand Iqbal (Site Director) | To have feedback on Water, Sanitation, and Hygiene (WASH) facilities across the site sanitation practices | All GSK employees across facilities potentially affected by droughts/dry seasons. | Gather feedback on current measures and suggestions for improvement. Highlight specific areas requiring immediate intervention or support | Demonstrates GSK's commitment to environmental and social responsibility | N/A (Journey Goes-On)
4 | Water Balance and Water Costs | Physical | No | A proper water balance is needed to manage water efficiently, understand water-related costs and trends. Not having a proper and updated water balance is likely to result in lost opportunity to optimise the water consumption and effectively meet GSK's water goals. | 3 | 3 | 9 | 1. Develop a water balance map using a scientific map by ensuring that all water inflows and outflows have been accounted for end-to-end including water usage in utilities. |  | 2025-08-25 | Done |  | Khurshand Iqbal (Site Director) | To develop a comprehensive water balance map for GSK facilities, ensuring accurate accounting of all water inflows, outflows, and usage across utilities to enable informed water management decisions, minimize wastage, and improve sustainability practices. | Collect quantitative data on water inflows and outflows for each facility. Identify water-intensive processes and utilities | Create a visual map illustrating the water balance across the facility | Identify key areas of inefficiency or water loss. | Done
[8 empty] | 2. Site should check for water losses and include the same in the water balance map. Formulate a plan to determine how these losses will be eliminated, wherever possible. |  | 2025-08-25 | Done | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To identify, quantify, and address water losses across GSK sites by incorporating detailed data into the water balance map and formulating a plan to eliminate or minimize these losses wherever feasible, thereby optimizing water usage and improving sustainability | Include all potential sources of water loss, such as leaks, evaporation, inefficient processes, and unaccounted discharge points, in the water balance map | Quantify water losses as part of the site-level water balance map | Identify key areas of inefficiency or water loss. | Done
[8 empty] | 3. Site to consider developing separate water balance maps for indicating high and low variances 3.1 Continue periodically reviewing and updating Site water balance map as per current water log data, process changes, other changes affecting the map. |  | 2025-08-25 | Done |  | Khurshand Iqbal (Site Director) | To identify, quantify, and address water losses across GSK sites by incorporating detailed data into the water balance map and formulating a plan to eliminate or minimize these losses wherever feasible, thereby optimizing water usage and improving sustainability | Include all potential sources of water loss, such as leaks, evaporation, inefficient processes, and unaccounted discharge points, in the water balance map | Quantify water losses as part of the site-level water balance map | Identify key areas of inefficiency or water loss. | Done
[8 empty] | 4. Identify additional areas in the Plant to install more water meters that may be beneficial for effective measurement of water used on-site |  | 2026-06-25 | In Progress | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To have trending on water Dashboard | 1) Tanker receiving & discharge meters will be planned to be shifted to RS485 Modbus Communication also finding oppurtunities for more metering across site for water consumptions 2) ETP Discharge Water to be converted to RS485 Modbus communication Target Completion: Dec-2026 | Quantify water losses as part of the site-level water balance map | Identify key areas of inefficiency or water loss. | In-Progress Estimated Budgeting: 15 KGBP PROJECT ID: OPEX
[8 empty] | 5. Site to include previously identified efficiency opportunities of Water Reuse/ Water Recycling in the Action Plan. |  | 2025-12-01 | In Progress |  | Khurshand Iqbal (Site Director) | To have trending on water Dashboard | 1) ETP Area Upgradation (Target Completion: Dec-25) (Project ID: 7500PK-IM-25052) 2) RO Reject Reuse (Solar Cleaning) (Target Completion: Nov-25) | N/A | Will help GSK in analysizing water challenges and take proactive measures | Ongoing Estimated ETP CAPEX: 71 KGBP Estimated RO Reject CAPEX: 23 KGBP
|  |  |  | Site should track its water costs closely and take it as an opportunity for continual improvement. Missing out on opportunities for optimization of water related costs, and savings. | 3 | 3 | 9 | 1. Site to track Water Related Costs including the Raw Water and Processing Costs. |  | 2026-01-01 | In Progress | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | GSK being aware of water challenges to be educated the community for any water associated challenges | Minimize OPEX Site Budget Water Governance Ensuring Regional Compliance Sustainability Goals | Future Projects identification | Will help GSK in analysizing water challenges and take proactive measures | In-Progress
5 | Extreme Weather and Incident Response | Physical + Reputational + Regulatory | Yes | Extreme weather conditions such as droughts or heavy rainfall may pose risk to business continuity, production loss, property damage, interruption to power supply damage to infrastructures, operational disruptions and compromise employee safety. Extreme weather (e.g., earthquakes, cyclones and droughts) may impact the supply chain and logistics which will disrupt raw material, finished good movement and lead to product shortages Opportunity for continual improvement. Without record of past incidents, Site will miss out on opportunities to improve its Incident Management System. | 2 | 3 | 6 | 1. Site to updated its Business Continuity Plan to cater for water shortage. Prioritize water uses which are crucial for the proper functioning of the Plant in the case of droughts or reduced water supply. |  | 2025-08-25 | Done |  | Khurshand Iqbal (Site Director) | To ensure uninterrupted operations of the plant during periods of drought or reduced water supply by updating the Business Continuity Plan (BCP) to prioritize critical water uses. | 1) Identify and Categorize Water Usage 2) Develop Water Contingency Strategies 3) Risk Mitigation Measures 4) Compliance & Sustainability | 1) Operational Rescillence 2) Enhanced Efficiency 3) Stakeholder Confidence | Business Continuity: Updating the BCP safeguards GSK's reputation and ensures consistent delivery of high-quality products to patients. Cost Effectiveness: Strategic water management reduces waste and operational costs. Sustainability: Supports GSK's commitment to environmental stewardship and resource conservation. Risk Reduction: Mitigates potential regulatory, financial, and reputational risks associated with water shortages. | Done
[8 empty] | 2. Site should develop dedicated storm water management plan. 3. Site should develop layout of pollution sources present on site. |  | 2025-06-25 | Done | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To ensure the effective collection, storage, and disposal of stormwater to prevent flooding, contamination, and environmental damage while enhancing site sustainability. | Assessment of Stormwater Flow: Analyze existing stormwater drainage systems and pathways. Identify high-risk areas for flooding or contamination on-site. Stormwater Infrastructure Development: Install or upgrade stormwater collection, storage, and drainage systems. Pollution Prevention in Stormwater: Implement filtration or sedimentation systems to reduce pollutants before stormwater discharge. . Compliance and Monitoring: Ensure adherence to local environmental regulations and GSK sustainability standards. | Flood Risk Mitigation: Reduced likelihood of operational disruptions caused by stormwater-related flooding. Pollution Control: Minimized environmental impact by preventing contaminated stormwater runoff. Operational Resilience: Enhanced site readiness and sustainability during extreme weather events | Environmental Protection: Preserves ecosystems by preventing stormwater pollution. Operational Stability: Reduces downtime and damage risks from flooding. Cost Savings: Avoids potential fines and remediation costs from environmental non-compliance. Sustainability Leadership: Strengthens GSK's reputation as an environmentally responsible organization | Done
[5 empty] | 2 | 3 | 6 | Site strom water management strategy to be reviewed for improvement areas |  | 2025-08-25 | Done | Minhal Raza (Country EHS Manager) | Khurshand Iqbal (Site Director) | To ensure for chemical storage and containment areas, walkways, and parking areas to ensure operational safety, environmental compliance. | The primary targets of this initiative include establishing clear communication that Life safety is the first priority of GSK | The development of (IH & EHS) Annual Inspection Visit will lead to improved safety standards across the site, minimizing risks of chemical spills, contamination, and accidents | This initiative Proactive audits will help GSK and reputational damage due to non-compliance while safeguarding nearby ecosystems from contamination | Done
6 | Stakeholder Engagement | Reputational | No | Lack of engagement between the Site and the key stakeholders would result in the Site missing out on opportunities to proactively identify various water-related issues in the catchment | 3 | 3 | 9 | 1. Formulate a list of key stakeholders in the area |  | 2025-07-01 | Done | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To achieve water targets and seek more initiatives as part of Water Savings | Reducing Water Footprints | N/A | Will help in achieving water waterfall targets as part of sustainability initiative from GSK Regional Team | Done
[8 empty] | 2. Based on above list, Site should develop a formal Stakeholder Engagement Plan. |  | 2025-07-25 | Done | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To achieve water targets and seek more initiatives as part of Water Savings | Reducing Water Footprints | N/A | Will help in achieving water waterfall targets as part of sustainability initiative from GSK Regional Team | Done
[8 empty] | 3.Communicate with relevant stakeholders about activities taken up by Site/GSK for the greater good (e.g., water conservation measures). |  | 2025-12-25 | In Progress | Ali Asim Hasan (Utilities Engineer) | Khurshand Iqbal (Site Director) | To achieve water targets and seek more initiatives as part of Water Savings | Reducing Water Footprints | N/A | Will help in achieving water waterfall targets as part of sustainability initiative from GSK Regional Team | In-Progress
7 | Indirect Water Use | Physical | No | Not understanding the water risks faced by suppliers and/or outsourced services may present a business continuity risk. Changes in supplier's water availability may disrupt the raw material and finished good movement and supply and lead to product shortages. | 2 | 3 | 6 | 1. Periodically monitor suppliers' response to water stewardship related actions and evaluate risks associated with decline in water availability/quality (e.g., does supplier have emergency response plans for water-related risks). Make this as a part of supplier management plan. |  | 2025-12-25 | Done | Sheraz Khan (Site Procurement Manager) | Khurshand Iqbal (Site Director) | To ensure uninterrupted water supplies for the site & acceptable water quality | To comply GSK Water quality parameters | Team is educated for complying the water quality parameters | Standardize the water quality parameters | Done
[8 empty] | 2. Identify key suppliers to engage with to understand overall water footprint and explore water consumption reduction options. Interact with vendors and seek information on their water usage and risks. |  | 2025-12-25 | In Progress | Sheraz Khan (Site Procurement Manager) | Khurshand Iqbal (Site Director) | To achieve water targets and seek more initiatives as part of Water Savings | Reducing Water Footprints | N/A | Will help in achieving water waterfall targets as part of sustainability initiative from GSK Regional Team | In-Progress